## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| school management software | kawthar | 2020-06-05 | 2020-07-05 |  | 60% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1: Requirment Mapping | Requirment | kawthar |  | 2020-06-05 | 2020-06-10 | 5 | Complete
| Feature 1: Map out the features required |  | rose | 2 | 2020-06-05 | 2020-06-08 | 3 | Complete
| Feature 2: Map out the users and requirment |  | batool | 1 | 2020-06-08 | 2020-06-09 | 1 | Complete
| Feature 3: map the reports required |  | rose | 1 | 2020-06-09 | 2020-06-10 | 1 | Complete
| Sprint 2: Feature Desiging | Feature | kawthar |  | 2020-06-12 | 2020-06-24 | 12 | Complete
| Feature 4: Desigin the interface feature |  | kawthar | 3 | 2020-06-12 | 2020-06-19 | 7 | Complete
| Feature 5: Desigin the the reports , dashboards and charts |  | batool | 2 | 2020-06-19 | 2020-06-22 | 3 | Complete
| Feature 6:Desigin the response time |  | rose | 1 | 2020-06-22 | 2020-06-24 | 6 | Overdue
| Sprint 3: Code Writing | Feature | rose |  | 2020-06-28 | 2020-07-05 | 10 | In Progress
| Feature 7: Write the code for the interface |  | batool | 1 | 2020-06-28 | 2020-06-30 | 2 | In Progress
| Feature 8: Write the code for the reports , dashboards and charts |  | batool | 1 | 2020-06-30 | 2020-07-03 | 7 | Not Started
| Feature 9: Write the code for the Al feature |  | kawthar | 1 | 2020-07-03 | 2020-07-04 | 1 | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.